## Todo List
To-do list
To be completed by: |  | 2025-10-24 |  | Name: Theophilus Bassaw
Deadline: |  | 2025-10-24 |  | Date: 10/26/2025
Homework 3
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Assign Partners | 2025-10-17 | 2025-10-17 | 2025-10-17 | 1
95% | Create Propositions | 2025-10-17 | 2025-10-24 | 2025-10-26 | 7 | Deadline extended by two days.
95% | Record Group Videos & Youtube Uploads | 2025-10-17 | 2025-10-24 | 2025-10-26 | 7 | Theo & Prachi recorded separately due to timing on Prachi's part. Deadline extended by two days.
95% | Homework Submission | 2025-10-17 | 2025-10-24 | 2025-10-26 | 7 | Deadline extended by two days.